## Sheet1
Risk Analysis
Design
Requirements
Prototype
Coding / Building
Testing
| Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
|  | Client Meeting |  | Client Meeting |  | Client Meeting |  |  | Client Meeting |  | Client Meeting
| Week 2 | risk analysis, design, and gathering general requirements
| Week 3 | risk analysis, design, and gathering general requirements
| Week 4 | risk analysis, design, constructing prototype for next client meeting
| Week 5 | risk analysis, design, gather general requirements, present rough prototype
| Week 6 | design, gathering more requirements
| Week 7 | design, gatheing more requirements, present prototype in client meeting
| Week 8 | create more detailed prototype
| Week 9 | create more detailed prototype
| Week 10 | present detailed prototype, confirm final requirements, begin coding 'skeleton', test.
| Week 11 | building and testing
| Week 12 | building and testing
| Week 13 | building and testing